## Sheet1
Code	Estimation (h)	Description
AT-001	1	move the solution to vs2012.
AT-002	1	move the solution on git.
AT-003	20	solve the problem with saving the datetimes into db.
		possible outcomes:
		- revert to ado.net
		- move to entity framework. maybe it works. (?)
		- find a clever solution (should not be a hack) to still use nhibernate.
AT-004	2	bug fix: when the "Pause" popup is displayed, if the user locks the computer, ActiveTime freezes.
AT-007	4	as a user i want to see the comments in the main window. (and not in a different window as it is now.)
AT-005	4	as a user i want to see, in the list of activity, with blue and aligned to left the periods of time when i've been active and with red and aligned to right the periods of time when i've been away.
AT-006	4	as a user i want to have a check-box to make the inactive periods visible or not in the list of activity.
AT-008	6	as a user i want to be able to manually add new active periods.
AT-009	4	as a user i want to be able to manually change the limits of the existing active periods.
AT-010	1	as a user i want to be able to manually delete active periods.
AT-011	(?)	(?) as a user i want to be able to set comments on the entire day (as it was until now), but also i want to be able to set comments on specific periods of time.